## Sheet1
Phase | Stage | Work_Package | Activities
Concept | Opportunity Screening | Screen Opportunities for strategic fit | High-level screen of each opportunity for strategic fit
Concept | Opportunity Screening | Screen Opportunities for strategic fit | Retain, discard, park opportunities.
Concept | Opportunity Screening | Identify Needs of stakeholders | Identify needs of the organisation
Concept | Opportunity Screening | Identify Needs of stakeholders | Develop or update scoring criteria to match opportunities to needs
Concept | Opportunity Screening | Review and collect supporting Data | Collect additional supporting data if required
Concept | Opportunity Screening | Review and collect supporting Data | Compile Opportunity Definition document
Concept | Opportunity Screening | Prioritise Opportunities applying scoring tool | Screening Committee Scores Opportunities
Concept | Opportunity Screening | Prioritise Opportunities applying scoring tool | Update database and assign "Go" / "No-Go" projects
Concept | Opportunity Screening | Prioritise Opportunities applying scoring tool | Assign a project number and enter into project funnel
Concept | Opportunity Screening | Prioritise Opportunities applying scoring tool | Identify resources required for Pre-Feasibility Stage
Concept | Opportunity Screening | Prioritise Opportunities applying scoring tool | Submit opportunities and threats to portfolio management process
Concept | Opportunity Screening | Prioritise Opportunities applying scoring tool | Identify stakeholders
Concept | Opportunity Screening | Submit Opportunities to Investment Portfolio Process | Prepare, consolidate and quality approve all opportunity material
Concept | Opportunity Screening | Submit Opportunities to Investment Portfolio Process | Submit all material to Investment Portfolio Committee
Concept | Opportunity Screening | Submit Opportunities to Investment Portfolio Process | Receive approved opportunities / projects from Investment Portfolio Committee
Concept | Opportunity Screening | Develop Pre-Feasibility Plan | Identify and Commit resources required for Pre-Feasibility Stage
Concept | Opportunity Screening | Develop Pre-Feasibility Plan | Project Concept and Scope
Concept | Opportunity Screening | Develop Pre-Feasibility Plan | Draft high-level Pre-Feasibility implementation plan
Concept | Pre Feasabillity | Project Definition : Project Brief
Concept | Pre Feasabillity | Project Definition : Project Brief
Concept | Pre Feasabillity | Project Definition : Project Brief
Concept | Pre Feasabillity | Project Definition : Project Brief
Concept | Pre Feasabillity | Project Definition : Project Brief
Concept | Pre Feasabillity | Project Definition : Project Brief
Concept | Pre Feasabillity | Project Definition : Project Brief
Concept | Pre Feasabillity | Establish the Core Project Team. | Define the Core Team governance structure and the key role players.
Concept | Pre Feasabillity | Establish the Core Project Team. | Appoint and onboard the Core Project Team.
Concept | Pre Feasabillity | Establish the Core Project Team. | Define and develop the Pre-Feasibility and Feasibility Implementation Plan.
Concept | Pre Feasabillity | Perform Concept Design | Review externalities, constraints and interfaces
Concept | Pre Feasabillity | Perform Concept Design | Define required operational capability
Concept | Pre Feasabillity | Perform Concept Design | Select technical alternatives
Concept | Pre Feasabillity | Perform Concept Design | Prepare preliminary designs and preliminary technical specifications
Concept | Pre Feasabillity | Perform Concept Design | Evaluate designs for strategic fit, fatal flaws, performance within system and environmental constraints
Concept | Pre Feasabillity | Perform Concept Design | Select best solution/s for Feasibility Study
Concept | Pre Feasabillity | Perform Concept Design | Commercial Project Sourcing - Market Intelligence and sourcing solutions
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Sponsor | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Sponsor | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Sponsor | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Sponsor | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Sponsor | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Sponsor | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Sponsor | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Board | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Board | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Board | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Board | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Board | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Board | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Board | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Manager | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Manager | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Manager | Conduct Interviews
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Manager | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Manager | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Manager | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Manager | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Administrator | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Administrator | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Administrator | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Administrator | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Administrator | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Administrator | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Administrator | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Quality Manager | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Quality Manager | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Quality Manager | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Quality Manager | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Quality Manager | Conduct Interviews
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Quality Manager | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Quality Manager | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Procurement Manager | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Procurement Manager | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Procurement Manager | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Procurement Manager | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Procurement Manager | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Procurement Manager | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Procurement Manager | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Communications Manager | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Communications Manager | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Communications Manager | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Communications Manager | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Communications Manager | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Communications Manager | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Communications Manager | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Office Manager | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Office Manager | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Office Manager | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Office Manager | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Office Manager | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Office Manager | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Office Manager | Remuneration
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Team Member | General Purpose of the role
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Team Member | Detailed Responsibillities
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Team Member | Relationship to other roles in the organisation
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Team Member | Skills Experience and qualifications
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Team Member | Perfromance Criteria
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Team Member | General work environment
Concept | Pre Feasabillity | Appoint the project team: List and define The Project roles: Project Team Member | Remuneration
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Review job analysis
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Draft Job Descriptions
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Review organisation structure and job descriptions
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Decide on recruitment method
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Place Advertisements
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Review Applicants
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Conduct Interviews
Concept | Pre Feasabillity | Appoint the project team: Identify Recruitment Process | Make Appointments
Concept | Pre Feasabillity | Perform base infrastructure assessment | Determine all inputs required
Concept | Pre Feasabillity | Perform base infrastructure assessment | Sites investigated
Concept | Pre Feasabillity | Perform base infrastructure assessment | Assess alternatives
Concept | Pre Feasabillity | Perform base infrastructure assessment | Identify and quantify fatal flaws
Concept | Pre Feasabillity | Perform base infrastructure assessment | Draft Base Infrastructure Development Plan
Concept | Pre Feasabillity | Determine Legal and Regulatory requirements | Identify all licensing, permitting requirements and timing
Concept | Pre Feasabillity | Determine Legal and Regulatory requirements | Compile list of required licences and permits
Concept | Pre Feasabillity | Determine Legal and Regulatory requirements | Draft high-level schedule of project activities
Concept | Pre Feasabillity | Perform stakeholder needs impact assessment | Perform regional (SADC) economic assessment
Concept | Pre Feasabillity | Perform stakeholder needs impact assessment | Perform local economic assessment
Concept | Pre Feasabillity | Perform stakeholder needs impact assessment | Determine stakeholders needs and impact assessment
Concept | Pre Feasabillity | Perform stakeholder needs impact assessment | EIA Scoping and public participation
Concept | Pre Feasabillity | Perform stakeholder needs impact assessment | Commercial Project Sourcing - Market Intelligence and sourcing solutions
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Identify and collate all input variables
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Define and understand market demand analysis
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Compile base case Data Book
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Develop financial information and options
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Risk analysis and mitigation. Perform fatal flaw analysis
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Assess site and technical solution alternatives
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Perform Economic Feasibility Analysis and Recommendation
Concept | Pre Feasabillity | Construct a preliminary Business Case and Risk Assessment | Provide Commercial support to construct a prelimenary business case and risk assessment
Concept | Pre Feasabillity | Identify financial and commercial structures | Identify commercial and funding options
Concept | Pre Feasabillity | Identify financial and commercial structures | Assess alternatives
Concept | Pre Feasabillity | Identify financial and commercial structures | Structure commercial and funding solution
Concept | Pre Feasabillity | Identify financial and commercial structures | Providing Commercial input required in Pre-feasibility phase
Concept | Pre Feasabillity | Partner Selection | Pre-Qualification of Partners (Excluding contractors)
Concept | Pre Feasabillity | Partner Selection | Due Diligence
Concept | Pre Feasabillity | Partner Selection | Negotiation
Concept | Pre Feasabillity | Partner Selection | Provide sourcing and commercial support for partner selection
Concept | Pre Feasabillity | Screen, prioritise and discard opportunities | Prepare and present business case and options to investment portfolio process
Concept | Pre Feasabillity | Screen, prioritise and discard opportunities | Screen and prioritise projects and release to Feasibility Stage
Concept | Pre Feasabillity | Screen, prioritise and discard opportunities | Update project pipeline / funnel.
Concept | Pre Feasabillity | Initiate high-level project development planning | Identify all project inputs and outputs
Concept | Pre Feasabillity | Initiate high-level project development planning | Define Feasibility Study and Scope
Concept | Pre Feasabillity | Initiate high-level project development planning | Define and scope EIA Plan
Concept | Pre Feasabillity | Initiate high-level project development planning | Prepare Feasibility and draft Project Budget
Concept | Pre Feasabillity | Initiate high-level project development planning | Produce Project Charter and Scope Document
Concept | Pre Feasabillity | Initiate high-level project development planning | Establish Commercial project controls for all phases
Definition | Feasabillity | Undertake a feasabillity study: Research the business problem | Data collection
Definition | Feasabillity | Undertake a feasabillity study: Research the business problem | Data analysis
Definition | Feasabillity | Undertake a feasabillity study: Research the business problem | Identify contributing factors
Definition | Feasabillity | Undertake a feasabillity study: Research the business problem | Identify the root cause
Definition | Feasabillity | Undertake a feasabillity study: List the key business drivers
Definition | Feasabillity | Undertake a feasabillity study: List the key business drivers | Changes in PESTE
Definition | Feasabillity | Undertake a feasabillity study: List the key business drivers | Competitive advantage
Definition | Feasabillity | Undertake a feasabillity study: List the key business drivers | A business plan or milestone
Definition | Feasabillity | Undertake a feasabillity study: Define business requirements
Definition | Feasabillity | Undertake a feasabillity study: Define business requirements | New technology development
Definition | Feasabillity | Undertake a feasabillity study: Define business requirements | New Processes and procedures
Definition | Feasabillity | Undertake a feasabillity study: Define business requirements | New Products or services
Definition | Feasabillity | Undertake a feasabillity study: Solution Development
Definition | Feasabillity | Undertake a feasabillity study: Solution Development | Develop list of altrernatives ITO Quantify Benefits
Definition | Feasabillity | Undertake a feasabillity study: Solution Development | Identify Possible solutions
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions: Undertake assessment
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions: Undertake assessment | Scope results
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions: Undertake assessment | Identify risks
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions: Undertake assessment | Identify issues
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions: Undertake assessment | List any assumptions
Definition | Feasabillity | Undertake a feasabillity study: Undertake a feasabillity study: Feasabillity of alternative sollutions
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions | Rank feasabillity results
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions | Identify best alternative
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions : Choose best alternative
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions : Choose best alternative | Rank the feasabillity results
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions : Choose best alternative | Interpret the feasabillity reults
Definition | Feasabillity | Undertake a feasabillity study: Feasabillity of alternative sollutions : Choose best alternative | Choose best alternative
Definition | Feasabillity | Undertake a feasabillity study: Undertake a feasabillity study: implementation approach
Definition | Feasabillity | Undertake a feasabillity study: implementation approach | implementation approach
Definition | Feasabillity | Undertake a feasabillity study: implementation approach | Partner selection
Definition | Feasabillity | Structure DCO & PMO Contract | Confirm Contract condition and SLA and Rates Agreements
Definition | Feasabillity | Structure DCO & PMO Contract | Identify contract type
Definition | Feasabillity | Structure DCO & PMO Contract | Compile PM Proposal (includes structures etc)
Definition | Feasabillity | Structure DCO & PMO Contract | Evaluate and Clarify Proposal
Definition | Feasabillity | Structure DCO & PMO Contract | Negotiation
Definition | Feasabillity | Structure DCO & PMO Contract | Compile contract
Definition | Feasabillity | Structure DCO & PMO Contract | Obtain Relevant Governance Approval
Definition | Feasabillity | Structure DCO & PMO Contract | Award Contracts
Definition | Feasabillity | Execute EIA, Regulatory and Legal
Definition | Feasabillity | Execute EIA, Regulatory and Legal | Identify and Appoint Independent EIA Consultants
Definition | Feasabillity | Execute EIA, Regulatory and Legal | Conduct EIA and Public Awareness
Definition | Feasabillity | Execute EIA, Regulatory and Legal | Evaluate EIA Report
Definition | Feasabillity | Execute EIA, Regulatory and Legal | Request EIA Approval
Definition | Feasabillity | Execute EIA, Regulatory and Legal | Obtain EA
Definition | Feasabillity | Execute EIA, Regulatory and Legal | Obtain Permit to take Water
Definition | Feasabillity | Execute EIA, Regulatory and Legal | Confirm Electricity Supply Licence
Definition | Feasabillity | Produce (URS) User Requirement Specs.
Definition | Feasabillity | Produce (URS) User Requirement Specs. | Scope URS Process
Definition | Feasabillity | Produce (URS) User Requirement Specs. | Define required operational capability, location, primary energy, and project requirements.
Definition | Feasabillity | Produce (URS) User Requirement Specs. | Document URS
Definition | Feasabillity | Produce (URS) User Requirement Specs. | Obtain Applicable Approvals
Definition | Feasabillity | Produce (URS) User Requirement Specs. | Issue URS to PO / ED Engineering
Definition | Feasabillity | Perform Basic Design
Definition | Feasabillity | Perform Basic Design | Gather and Review Requirements (URS, regulatory, environmental)
Definition | Feasabillity | Perform Basic Design | Prepare Basic Design Plan
Definition | Feasabillity | Perform Basic Design | Select Engineering Codes and Standards
Definition | Feasabillity | Perform Basic Design | Perform Preliminary Design (Systems and Sub-systems)
Definition | Feasabillity | Perform Basic Design | Prepare Cost Estimates
Definition | Feasabillity | Perform Basic Design | Perform Constructability Reviews
Definition | Feasabillity | Perform Basic Design | Evaluate Technical Alternatives (economics, performance, safety, logistics support, environmental, supply capability etc.) Identify OEMs.
Definition | Feasabillity | Perform Basic Design | Perform Value Engineering
Definition | Feasabillity | Perform Basic Design | Commercial Support to Value Engineering.
Definition | Feasabillity | Perform Basic Design | Integrate designs
Definition | Feasabillity | Perform Basic Design | Final Design Review, Challenge and Approval
Definition | Feasabillity | Perform Basic Design | Issue Engineering Specs and Cost Analyse to PO
Definition | Feasabillity | Perform Basic Design | Provide Commercial input into cost estimate of the Basic Design.
Definition | Feasabillity | Develop Contracting Strategy
Definition | Feasabillity | Develop Contracting Strategy | Develop Contracting Strategy
Definition | Feasabillity | Develop Contracting Strategy | Determine preferred Contract Execution Models
Definition | Feasabillity | Develop Contracting Strategy | Undertake Contract Strategy Risk Assessment
Definition | Feasabillity | Develop Contracting Strategy | Select Preferred Contract Type and form of Contract
Definition | Feasabillity | Develop Contracting Strategy | Obtain Commercial Approval
Definition | Feasabillity | Establish PMO & 3rd Party Structures
Definition | Feasabillity | Establish PMO & 3rd Party Structures | Provide sourcing and commercial input and support for PMO & 3rd Party selection
Definition | Feasabillity | Establish PMO & 3rd Party Structures | Investigate and agree commercial structures
Definition | Feasabillity | Establish PMO & 3rd Party Structures | Identify potential partners - RFI's
Definition | Feasabillity | Establish PMO & 3rd Party Structures | Receive and Evaluate and short-list
Definition | Feasabillity | Establish PMO & 3rd Party Structures | Draft Memorandum of Understanding
Definition | Feasabillity | Establish PMO & 3rd Party Structures | Sign MOU
Definition | Feasabillity | Preliminary Site Selection
Definition | Feasabillity | Preliminary Site Selection | Short List sites
Definition | Feasabillity | Preliminary Site Selection | Geotech Analysis
Definition | Feasabillity | Preliminary Site Selection | Integrate Site Options with Primary Energy Options
Definition | Feasabillity | Preliminary Site Selection | Integrate Site Options with Cooling and Service Support Options
Definition | Feasabillity | Preliminary Site Selection | Integrate Site Options with Transmission
Definition | Feasabillity | Preliminary Site Selection | Determine Site Support Infrastructure
Definition | Feasabillity | Preliminary Site Selection | Draft Letters of Intent
Definition | Feasabillity | Prepare and Distribute RFI's
Definition | Feasabillity | Prepare and Distribute RFI's | Verify Supply Base, Prepare and distribute RFP / EOL
Definition | Feasabillity | Prepare and Distribute RFI's | Compile Requests for Information / Requests for Proposals
Definition | Feasabillity | Prepare and Distribute RFI's | Perform a SQUAD Check
Definition | Feasabillity | Prepare and Distribute RFI's | Issue RFI's
Definition | Feasabillity | Prepare and Distribute RFI's | Evaluate RFI's
Definition | Feasabillity | Prepare and Distribute RFI's | Prequalify and Evaluate Potential Suppliers
Definition | Feasabillity | Prepare and Distribute RFI's | Short List Potential Suppliers
Definition | Feasabillity | Establish Project Management Support
Definition | Feasabillity | Establish Project Management Support | Establish Project Management Structure
Definition | Feasabillity | Establish Project Management Support | Identify Required Resources
Definition | Feasabillity | Establish Project Management Support | Establish Project Support Infrastructure
Definition | Feasabillity | Establish Project Management Support | Appoint Resources with a Phased Approach
Definition | Feasabillity | Establish Project Management Support | Confirm Project Methodology and Close Capability Training Gaps with Staff
Definition | Feasabillity | Establish Project Management Support | Establish Project Sourcing team and resources for the execution phase.
Definition | Feasabillity | Establish Client Office Management Support
Definition | Feasabillity | Establish Client Office Management Support | Establish CO Management Structure
Definition | Feasabillity | Establish Client Office Management Support | Identify Required Resources
Definition | Feasabillity | Establish Client Office Management Support | Establish CO Support Infrastructure
Definition | Feasabillity | Establish Client Office Management Support | Appoint Resources with a Phased Approach
Definition | Feasabillity | Develop Project Charter: Initiation Planning | Plan Start up stage activities
Definition | Feasabillity | Develop Project Charter: Initiation Planning | Identify Corporate or Programme Planning Standards
Definition | Feasabillity | Develop Project Charter: Start up definition | Decide on project mandate
Definition | Feasabillity | Develop Project Charter: Start up definition | Hold decision meeting on project mandate
Definition | Feasabillity | Develop Project Charter: Start up definition | Conduct a Job Analysis
Definition | Feasabillity | Develop Project Charter: Start up definition | PM Staff Appointments
Definition | Feasabillity | Develop Project Charter: Start up definition | Charter / PID / Initiation Document
Definition | Feasabillity | Develop Project Charter: Start up definition | Charter / PID / Initiation Document
Definition | Feasabillity | Develop Project Charter: Start up definition | Identify the project vision
Definition | Feasabillity | Develop Project Charter: Start up definition | Analyze project announcement and develop project vision
Definition | Feasabillity | Develop Project Charter: Start up definition | Analyze project announcement and develop project vision
Definition | Feasabillity | Develop Project Charter: Start up definition | Analyze project announcement
Definition | Feasabillity | Develop Project Charter: Start up definition | Clear up uncertainties
Definition | Feasabillity | Develop Project Charter: Start up definition | Develop project vision
Definition | Feasabillity | Develop Project Charter: Start up definition | Define initialization process
Definition | Feasabillity | Develop Project Charter: Start up definition | SMART
Definition | Feasabillity | Develop Project Charter: Start up definition | Idnetify or define Milestones
Definition | Feasabillity | Develop Project Charter: Start up definition | Develop Project Scoope
Definition | Feasabillity | Develop Project Charter: Start up definition | Record project description and project environment
Definition | Feasabillity | Develop Project Charter: Start up definition | Job Descriptions Produced
Definition | Feasabillity | Develop Project Charter: Start up definition | Job Descriptions Produced
Definition | Feasabillity | Develop Project Charter: Start up definition | Determine process model
Definition | Feasabillity | Develop Project Charter: Start up definition | Determine project flow
Definition | Feasabillity | Develop Project Charter: Start up definition | Assign project name
Definition | Feasabillity | Develop Project Charter: Start up definition | Draft project marketing concept
Definition | Feasabillity | Develop Project Charter: Start up definition | Inform Management about project
Definition | Feasabillity | Develop Project Charter: Describe the Project Organisation | Establish Customer Relations
Definition | Feasabillity | Develop Project Charter: Identify Roles and responsibillities | Draft Parics Chart
Definition | Feasabillity | Develop Project Charter: Identify Roles and responsibillities | Define who does what
Definition | Feasabillity | Develop Project Charter: Describe the Project Organisation | Identify stakeholders
Definition | Feasabillity | Develop Project Charter: Describe the Project Organisation | Identify Responsibillities
Definition | Feasabillity | Develop Project Charter: Describe the Project Organisation | Develop Project OBS
Definition | Feasabillity | Develop Project Charter: List the project roles | Conduct a Job Analysis administration
Definition | Feasabillity | Develop Project Charter: Define the roles and responsibillities | Conduct a Job Analysis Governance
Definition | Feasabillity | Develop Project Charter: Identify the recruitment process | Conduct a Job Analysis administration
Definition | Feasabillity | Develop Project Charter: Define OBS | Designing a Project Management Team
Definition | Feasabillity | Develop Project Charter: Conduct a Job Analysis | Appoint the project team
Definition | Feasabillity | Develop Project Charter: Conduct a Job Analysis | Appointing a Project Management Team
Definition | Feasabillity | Develop Project Charter: Determine project organization | Determine project organization
Definition | Feasabillity | Develop Project Charter: Conduct a Job Analysis | List the project roles
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | administration
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Time Management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Cost Management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Change Management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Risk Management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Issue management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Procurement management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Acceptance management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Communications Management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Phase Reviews
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Auditing and Compliance
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Supporting Staff
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Providing Tools
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Documentation management
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | general Administration
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Undertake Closure reviews
Definition | Feasabillity | Project Start Up Definition: Define the role of the project office | Time Management
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Resource and locate the project office
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Project Administrator
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Quality Manager
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Risk Manager
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Change Manager
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Procurement Manager
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Communications Manager
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Plan Physical Location of offices
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Acquire Office Space
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Craete list of office requirements
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Acquire Furniture and Fitments
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Plan telecoms Requirements
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Plan It Infrastructure
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Plan Access control
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Identify Physical Space Requirements and Premises
Definition | Feasabillity | Project Start Up Definition: Resource and locate the project office | Draft and submit Office Budget
Definition | Feasabillity | Project Start Up Definition: Create the tools to run the project office | Create the tools to run the project office
Definition | Feasabillity | Project Start Up Definition: Identify Necessary standards, methods and Tools | Standards
Definition | Feasabillity | Project Start Up Definition: Create the tools to run the project office | Methodologies
Definition | Feasabillity | Project Start Up Definition: Create the tools to run the project office | Project Planning Tools
Definition | Feasabillity | Project Start Up Definition: Create the tools to run the project office | Resource Planning Tools
Definition | Feasabillity | Project Start Up Definition: Create the tools to run the project office | Financial Planning Tools
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Time Management
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Cost Mangement
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Quality Management
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Change Management
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Risk management
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Issue Management
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Procurement Management
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Communications Management
Definition | Feasabillity | Project Start Up Definition: Create the Templates to run the project office | Acceptance management
Definition | Feasabillity | Deal Structuring and Bankable Report
Definition | Feasabillity | Deal Structuring and Bankable Report | Technical feasibility
Definition | Feasabillity | Deal Structuring and Bankable Report | Commercial and economic viability
Definition | Feasabillity | Deal Structuring and Bankable Report | Legal framework
Definition | Feasabillity | Deal Structuring and Bankable Report | Financeability of project
Definition | Feasabillity | Deal Structuring and Bankable Report | Environmental acceptability
Definition | Feasabillity | Deal Structuring and Bankable Report | Provide Commercial input to draft shareholder agreement or special purpose vehicle.
Definition | Feasabillity | Compile Business Case | Review all information from Feasibility Stage Activities
Definition | Feasabillity | Compile Business Case | Compile Business Case
Definition | Feasabillity | Compile Business Case | Obtain Approval for a Bankable Project
Definition | Feasabillity | Compile Business Case | Draft bid submission documents
Definition | Feasabillity | Compile Business Case | Commercial to provide input to Business Case compilation.
Definition | Business Plan | Develop Engineering Specifications
Definition | Business Plan | Develop Engineering Specifications | Review Contract Strategy and Basic Design Requirements
Definition | Business Plan | Develop Engineering Specifications | Group logical work packages
Definition | Business Plan | Develop Engineering Specifications | Develop and Select Technical Specifications
Definition | Business Plan | Develop Engineering Specifications | Structure Technical Integration between Work Packages
Definition | Business Plan | Develop Engineering Specifications | Review and Approve Technical Specifications
Definition | Business Plan | Develop Engineering Specifications | Commercial to Support Engineering Specification Development.
Definition | Business Plan | Finalise Regulatory and Legal Approvals
Definition | Business Plan | Finalise Regulatory and Legal Approvals | Obtain all Licences and Approvals
Definition | Business Plan | Finalise Regulatory and Legal Approvals | Interpret Licence Implications on Project Execution Requirements
Definition | Business Plan | Resolve Commercial and Financial Issues
Definition | Business Plan | Resolve Commercial and Financial Issues | Identify all Commercial and Financial Requirements
Definition | Business Plan | Resolve Commercial and Financial Issues | Develop and Establish Ownership Structure
Definition | Business Plan | Resolve Commercial and Financial Issues | Define Special Purpose Vehicle (SPV) structure
Definition | Business Plan | Resolve Commercial and Financial Issues | Finalise Financial Structure for Funding
Definition | Business Plan | Project Financial management
Definition | Business Plan | Project Financial management | Define Project Funding Structures
Definition | Business Plan | Project Financial management | Programme budget allocation
Definition | Business Plan | Project Procurement management
Definition | Business Plan | Project Procurement management | Define Project Commercial structures
Definition | Business Plan | Project Procurement management | Define Project Commercial structures
Definition | Business Plan | Project Execution Strategy
Definition | Business Plan | Project Execution Strategy | Finalise Project Resource Structure
Definition | Business Plan | Project Execution Strategy | Perform 1st Constructability Review
Definition | Business Plan | Project Execution Strategy | Develop Level 1 and 2 Project Schedule
Definition | Business Plan | Project Execution Strategy | Establish Configuration and Document Management Office per Project.
Definition | Business Plan | Project Execution Strategy | Define Project Methodology to be used and Software Support
Definition | Business Plan | Project Execution Strategy | Establish Project Standards and Procedures
Definition | Business Plan | Project Execution Strategy | Develop Project Cost Plan
Definition | Business Plan | Project Execution Strategy | Commercial input to Business Plan phase
Definition | Business Plan | Project Execution Strategy | Finalise Project Implementation Plan
Definition | Business Plan | Lifecycle Operation Plan
Definition | Business Plan | Lifecycle Operation Plan | Develop Governance Structure
Definition | Business Plan | Lifecycle Operation Plan | Develop Operations and Maintenance Methodology
Definition | Business Plan | Lifecycle Operation Plan | Identify Operation Structure
Definition | Business Plan | Lifecycle Operation Plan | Identify Supply Services
Definition | Business Plan | Lifecycle Operation Plan | Develop Plant Lifecycle Cost Plan
Definition | Business Plan | Initiate and Structure Project Set-Up
Definition | Business Plan | Initiate and Structure Project Set-Up | Initiate and establish the Project Set-Up Team.
Definition | Business Plan | Initiate and Structure Project Set-Up | Define and plan requirements and deliverables process and timeline.
Definition | Business Plan | Initiate and Structure Project Set-Up | Assign deliverables sub-project teams
Definition | Business Plan | Initiate and Structure Project Set-Up | Assist the Execution Project Manager to establish management team.
Definition | Business Plan | Initiate and Structure Project Set-Up | Establish the Project Office infrastructure and resources
Definition | Business Plan | Data Hand-Over to Execution | Compile and Consolidate the Project Definition Handover Pack
Definition | Business Plan | Data Hand-Over to Execution | Consolidate all Permits and Statutory and Legal Documents and Approvals
Definition | Business Plan | Data Hand-Over to Execution | Hand-Over / Transfer all Approvals, Data and Information to CED
Definition | Business Plan | Detailed Business Plan Developed
Definition | Business Plan | Detailed Business Plan Developed | Review all information from Business Plan Stage Activities
Definition | Business Plan | Detailed Business Plan Developed | Compile Business Plan
Definition | Business Plan | Detailed Business Plan Developed | Compile and Obtain Approval for ERA
Definition | Business Plan | Detailed Business Plan Developed | Prepare and submit Bid
Execution | Planning and Design | Project Start-Up | Project Manager and Core Team formally appointed (if not already done).
Execution | Planning and Design | Project Start-Up | Project governance organisation and procedures established.
Execution | Planning and Design | Project Start-Up | ICT Systems installed, configured and integrated with greater organisation
Execution | Planning and Design | Project Start-Up | Procedure manuals and operating procedures and processes developed
Execution | Planning and Design | Project Start-Up | Partnering and Team Building activities intitiated and managed
Execution | Planning and Design | Project Start-Up | Change management processes and activites activated.
Execution | Planning and Design | Establish Project Execution Org. Structure
Execution | Planning and Design | Establish Project Execution Org. Structure | Resource and Establish Project Office Infrastructure
Execution | Planning and Design | Establish Project Execution Org. Structure | Appoint Balance of Project Resources
Execution | Planning and Design | Establish Project Execution Org. Structure | Establish and Implement all Applicable Policies and Procedures
Execution | Planning and Design | Establish Project Execution Org. Structure | Establish Project Sourcing Execution Organisation Structure.
Execution | Planning and Design | Project Implementation Plan
Execution | Planning and Design | Project Implementation Plan | Review all Information from Project Execution Planning Stage
Execution | Planning and Design | Project Implementation Plan | Perform 2nd Constructability Review
Execution | Planning and Design | Project Implementation Plan | Update Level 1 & 2 Schedules and include Applicable Level 3 and 4 Items
Execution | Planning and Design | Project Implementation Plan | Compile Project Implementation Plan
Execution | Planning and Design | Project Implementation Plan | Obtain Approval for Project Implementation Plan
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define Product Packages
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define Work Packages
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define Tasks
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define Activities
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | List of Activities
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define WBS Numbering Structure and Codes
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define Work Packages
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | list the tasks
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Create a management schedule
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | List The project phases
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | List of Activities
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | list the tasks
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Activity Durations
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Identifying Activity Dependencies
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Schedule Activity Dependencies
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Determine taks dependencies Finish to start
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Determine taks dependencies Finish to finish
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Determine taks dependencies Start to start
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Determine taks dependencies Start to finish
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define Resources required for the execution of the tasks
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define requirements of identified resources
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Define Level of effort required by resources
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Labour
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Equipment
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Materials
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Activities
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Tasks
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Schedule
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Role
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Number
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | responsibillities
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Skills Experience and qualifications
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Start Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | End Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Item
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Amount
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Purpose
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Specification
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Start Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | End Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Item
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Amount
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Purpose
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Specification
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Start Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | End Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Schedule resources accrding to when needed
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Resources are available
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Changes in scope
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Funding availabillity
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Item
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Amount
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Purpose
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Specification
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Start Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | End Date
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Time
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | BUdget
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Resource availabillity
Execution | Planning and Design | Create the various execution plans : Scope, WBS and resources Planning | Activity Durations
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Purchases
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Leasing
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Rent
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Contracts
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Labour
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | External Procurements
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Office and administrative expenses
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Determine The Accounting Structure and Chart of accounts
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Ledger accounts tied to WBS Elements
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Open up accounts in accounting system
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Labour rate per hour
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Rental expenses per period
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Materials per quantity
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Create a financial plan Schedule the flow of funds in accordance with required payment times
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | List assumptions made during planning
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Resource availabillity
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Changes in scope
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Funding availabillity
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Purpose of the process
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Steps involved in undertaking the process
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Roels and responsibillities involved in process execution
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Templtes used in supporting the process
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Tools used in executing the process
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Time
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | BUdget
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Resource availabillity
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Detailed Funding and Call-Down Plan
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Update Cost Plan
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Compile Cash-Flow Forecast
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Develop and Implement Chart of Accounts
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Establish Forecast to Completion Process
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Commercial to Provide input to Call Down plan
Execution | Planning and Design | Create the various execution plans: Create a financial plan Categorise Expenses | Obtain Funding Plan Approval
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Identify ISO Standards
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Identify industry standards
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Identify Bodies of knowledge
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Identify Audit Standards
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Define Quality targets
Execution | Planning and Design | Create the various execution plans: Create a quality plan | requirements
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Deliverables
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Quality Criteria
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Qulity standards
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Create a Quality Assurance Plan
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Identify Quality Assurance Techniques Quality Reviews
Execution | Planning and Design | Create the various execution plans: Create a quality plan | reviews by external parties
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Determine Quality Performance
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Identify Methodologies
Execution | Planning and Design | Create the various execution plans: Create a quality plan | techniques
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Descriptions
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Frequencies
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Peer reviews
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Identify quality control techniques
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Documentation reviews
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Phase reviews
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Define the quality management process Purpose of the process
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Steps involved in undertaking the process
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Roles and responsibilities involved in undertaking the process
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Templates used to support the process
Execution | Planning and Design | Create the various execution plans: Create a quality plan | Tools used in executing the process
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Identify The Communications Stakeholders
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Project Sponsor
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Project Customer
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Project Board
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Project Manager
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Project Leader
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Team member
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Quality Manager
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Procurement Manager
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Communications Manager
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | PRoject Office Manager
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Business managers
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | External Organisations
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Stakeholders in accordance with PESTEL
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | requirements Message
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Medium
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Frequency
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Cosntruct a communications Schedule Stakeholder name
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Stakeholder role
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Stakeholder organisation
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Information requirement
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Frequency of communiations
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Message content
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Medium of communication
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Define the various communication processes Purpose of the process
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Steps involved in undertaking the process
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Roles and responsibilities involved in undertaking the process
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Templates used to support the process
Execution | Planning and Design | Create the various execution plans: Create a Communications plan | Tools used in executing the process
Execution | Planning and Design | Configuration management Implement configuration Planning
Execution | Planning and Design | Configuration management Implement configuration Planning | Verify and tailor CM plan
Execution | Planning and Design | Configuration management Implement configuration Planning | Verify and tailor CM
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan List Acceptance Critreria for Deliverables | Acceptance Standdards
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan List Acceptance Criteria for Processes | Time
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan List Acceptance Criteria for Processes | Cost
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan List Acceptance Criteria for Processes | Quality of Output
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan List Acceptance Criteria for Processes | Through Put
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan Create an accceptance schedule | Deliverable
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan | time Scale
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan | Define testing Method
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan | Identify Testers
Execution | Planning and Design | Create the various execution plans: Create an acceptance plan | Determine Testing Date
Execution | Planning and Design | Create the various execution plans: Create a risk plan Identify the risks | Run risk workshop
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Project Sponsor
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Project Manager
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Team member
Execution | Planning and Design | Create the various execution plans: Create a risk plan | suppliers
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Customers
Execution | Planning and Design | Create the various execution plans: Create a risk plan List The risk categories | Requirements
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Benefits realisation
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Schedule
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Budget
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Deliverables
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Scope
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Issues
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Suppliers
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Acceptance
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Communication
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Resources
Execution | Planning and Design | Create the various execution plans: Create a risk plan List The risk categories | Risk Category
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Risk Description
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Risk ID
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Relations ship to WBS Element
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify Likelihood of occurance | Rate Likelihood of occurance
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify Likelihood of occurance | Title
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify Likelihood of occurance | Score
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify Likelihood of occurance | Descriptions
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify Likelihood of occurance | Assess cross Impact
Execution | Planning and Design | Create the various execution plans: Create a risk plan Assign a priority | Risk ID
Execution | Planning and Design | Create the various execution plans: Create a risk plan Assign a priority | Likelihood score
Execution | Planning and Design | Create the various execution plans: Create a risk plan Assign a priority | Impact score
Execution | Planning and Design | Create the various execution plans: Create a risk plan Assign a priority | Priority score
Execution | Planning and Design | Create the various execution plans: Create a risk plan Assign a priority | Priority rating
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify impact | Title
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify impact | Score
Execution | Planning and Design | Create the various execution plans: Create a risk plan Quantify impact | Descriptions
Execution | Planning and Design | Create the various execution plans: Create a risk plan | Construct a risk schedule
Execution | Planning and Design | Create the various execution plans: Create a risk plan Compile risk register | Risk rating
Execution | Planning and Design | Create the various execution plans: Create a risk plan Compile risk register | Risk ID
Execution | Planning and Design | Create the various execution plans: Create a risk plan Compile risk register | Preventative actions
Execution | Planning and Design | Create the various execution plans: Create a risk plan Compile risk register | Resources to take action
Execution | Planning and Design | Create the various execution plans: Create a risk plan Compile risk register | Action Date
Execution | Planning and Design | Create the various execution plans: Create a risk plan Define the risk mangement process | Purpose of the process
Execution | Planning and Design | Create the various execution plans: Create a risk plan Define the risk mangement process | Steps involved in undertaking the process
Execution | Planning and Design | Create the various execution plans: Create a risk plan Define the risk mangement process | Roles and responsibilities involved in undertaking the process
Execution | Planning and Design | Create the various execution plans: Create a risk plan Define the risk mangement process | Templates used to support the process
Execution | Planning and Design | Create the various execution plans: Create a risk plan Define the risk mangement process | Tools used in executing the process
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Consider Buy vs Make Decision | Consider Buy vs Make Decision
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Create an Outsourcing / Procurement List | Products
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Create an Outsourcing / Procurement List | Services
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Create an Outsourcing / Procurement List | Results
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research market offerings | Research market offerings
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Create Procurement schedule | Selection of suppliers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Create Procurement schedule | Procurement of Items
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Create Procurement schedule | Managing supplier performance
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement Needs | Define Procurement Needs
Execution | Planning and Design | Create the various execution plans: Create a procurement plan List and describe each procurement Item | Item Description
Execution | Planning and Design | Create the various execution plans: Create a procurement plan List and describe each procurement Item | Justification
Execution | Planning and Design | Create the various execution plans: Create a procurement plan List and describe each procurement Item | Quantities
Execution | Planning and Design | Create the various execution plans: Create a procurement plan List and describe each procurement Item | Budgetted for
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | Research the market segment
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | What is the size of the relevant market segment
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | Number of suppliers that operate in this segment
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | Which supplier has the largest market segment
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | Which suppliers has the largets market share
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | Number of suppliers offering the required item
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | timeliness and availabillity of products
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Research the market offerings | risk associated with a specific supplier
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Define and validate the tendering process
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Issue RFI
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Document Statement of work (SOW)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Document Request for information (RFI)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Release tender documents (RFP & SOW)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Receive and evaluate tender documetns
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Rank, select and short list tenderers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Communicate appropreate information to all tenderers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Issue Request for Proposal ( RFP)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Document Request for proposal (RFP)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Receive and evaluate tender responses
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Select prefered tenderer
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Construct a procurement schedule | Contract with the winning tenderer in accordance with the selcted contract type and strategy
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Approving the SOW
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Monitor and evaluate the process
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Select prefered supplier
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Resolkves contractual issues
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Authorises final supplier contract
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Creating SOW, RFI, RFP
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Obtain approval for pre tender Document Release
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Collating responses
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Organising tender evaluation Process
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Co-select preferred suppliers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Notify insucsessful applicants
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Document supplier contracts
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define Procurement roles | Lead supplier negotiaations
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Document Statement of work | Issue RFI Document Statement of work
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFI Document Request for information
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Release tender documents (RFI & SOW)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Release tender documents (RFI & SOW)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Release tender documents (RFI & SOW)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Release tender documents (RFI & SOW)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Receive and evaluate tender responses
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Receive and evaluate tender responses
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Receive and evaluate tender responses
Execution | Planning and Design | Create the various execution plans: Create a procurement plan release tender Documents | Draft tender shortlist & notify suppliers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFP Update SOW
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFP Update SOW
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Issue RFP Update SOW
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process Issue RFP | Document Request for proposal (RFP)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Release tender documents (RFP & SOW)
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Receive and evaluate tender responses
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Define the tendering process | Select preferred tenderer and notify suppliers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Document supplier contracts: Draft agreement & Present to supplier
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Document supplier contracts: Define relationships
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Document supplier contracts: Define performance management & Measurement
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Document supplier contracts: Define dispute rsolotion process
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Document supplier contracts: specify : Deliverables
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Document supplier contracts: Specify : Responsibillities
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Document supplier contracts: Specify : terms and conditions of procurement
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Negotiate supplier contract: Negotiate Contract
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Negotiate supplier contract: Get agreement on mutually acceptable terms
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Sign Supplier contract: Formalise Contract Signing
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Initiate contractual obligations: Perform Contracts administration
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Initiate contractual obligations: Enforce Contractual Liabillities
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Contract with the suppliers Issue Contract | Initiate contractual obligations: Monitor Contratual terms and conditions
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Detailed Procurement and Contracting Plan | Establish a Supplier List with Reference to the Work Packages
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Detailed Procurement and Contracting Plan | Develop and Confirm Contracting Strategy
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Detailed Procurement and Contracting Plan | Confirm Contract Types and Form of Contracts
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Detailed Procurement and Contracting Plan | Confirm Applicable Policies and Procedures and Identify Approval Committees
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Detailed Procurement and Contracting Plan | Obtain Approval for Supplier List and Strategy
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Detailed Procurement and Contracting Plan | Develop Detailed Procurement and Contracting Plan
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Detailed Procurement and Contracting Plan | Execute Awareness among Suppliers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Pre-Qualify Suppliers | Review Quality Assurance Strategy in PIP
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Pre-Qualify Suppliers | Arrange Supplier Inspections and Terms of Reference
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Pre-Qualify Suppliers | Perform Quality Audit on all Short-Listed Suppliers
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Pre-Qualify Suppliers | Evaluate Outcomes
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Pre-Qualify Suppliers | Finalise Supplier Short-List
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Identify Long Lead Time Items - Obtain Permission to call for Tenders
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Develop Applicable Detailed Technical Specs.
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Develop Tender Enquiry Documents
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Issue Tender Enquiries
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Evaluate Submissions
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Clarify Details
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Select and Obtain Permission to Award Contract
Execution | Planning and Design | Create the various execution plans: Create a procurement plan Long Lead Time Items | Award Contracts
Execution | Planning and Design | Create the various execution plans: Create a change management plan
Execution | Planning and Design | Create the various execution plans: Create a change management plan | List the change management criteria
Execution | Planning and Design | Create the various execution plans: Create a change management plan | Define the change management process
Execution | Planning and Design | Create the various execution plans: Create a change management plan | Define the change management roles
Execution | Planning and Design | Create the various execution plans : Schedule Project Work
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | List assumptions made during planning Resource availabillity
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | List assumptions made during planning Resource availabillity
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | List assumptions made during planning changes in scope
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | List assumptions made during planning Funding
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | List planning constraints Budget and Cash Flow
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | List planning constraints Time
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | Determine Critical path / Critical Chain
Execution | Planning and Design | Create the various execution plans : Schedule Project Work | Construct Gannt Chart
Execution | Planning and Design | Concept Development
Execution | Planning and Design | Concept Development Develop Detailed Concept
Execution | Planning and Design | Concept Development Develop Detailed Concept | Determine detailed concept process
Execution | Planning and Design | Concept Development Develop Detailed Concept | Define and make available development environment
Execution | Planning and Design | Concept Development Develop Detailed Concept | Develop parameter system
Execution | Planning and Design | Concept Development Develop Detailed Concept | Develop extension concept
Execution | Planning and Design | Concept Development Develop Detailed Concept | Define interfaces
Execution | Planning and Design | Concept Development Develop Detailed Concept | Define IT infrastructure
Execution | Planning and Design | Concept Development Develop Detailed Concept | Develop authorization concept
Execution | Planning and Design | Concept Development Develop Detailed Concept | Verify profitability of detailed concept
Execution | Planning and Design | Concept Development Develop Detailed Concept | Hold decision meeting on detailed concept
Execution | Planning and Design | Scope Freeze
Execution | Planning and Design | Scope Freeze
Execution | Planning and Design | Design Freeze
Execution | Planning and Design | Design Freeze
Execution | Contracting and Procurement | Compile Balance of Enquiries
Execution | Contracting and Procurement | Compile Balance of Enquiries
Execution | Contracting and Procurement | Compile Balance of Enquiries | Identify balance of items to be Procured - Obtain Permission to call for Tenders
Execution | Contracting and Procurement | Compile Balance of Enquiries | Develop Applicable Detailed Technical Specs.
Execution | Contracting and Procurement | Compile Balance of Enquiries | Develop Tender Enquiry Documents
Execution | Contracting and Procurement | Compile Balance of Enquiries | Issue and Execution of Tender Enquiries
Execution | Contracting and Procurement | Compile Balance of Enquiries | Evaluate Submissions
Execution | Contracting and Procurement | Compile Balance of Enquiries | Clarify Details
Execution | Contracting and Procurement | Compile Balance of Enquiries | Select and Obtain Permission to Award Contract
Execution | Contracting and Procurement | Compile Balance of Enquiries | Award Contracts
Execution | Contracting and Procurement | Compile Balance of Enquiries | Financial Closure and Contract Signature
Execution | Contracting and Procurement | Update Project Implementation Plan
Execution | Contracting and Procurement | Update Project Implementation Plan
Execution | Contracting and Procurement | Update Project Implementation Plan | Include the Balance of all Information from Balance of Enquiries
Execution | Contracting and Procurement | Update Project Implementation Plan | Produce Procurement and Contracting Schedule
Execution | Contracting and Procurement | Update Project Implementation Plan | Produce Project Master Schedule
Execution | Contracting and Procurement | Update Project Implementation Plan | Update and finalise Funding Plan
Execution | Contracting and Procurement | Update Project Implementation Plan | Finalise Project Baseline
Execution | Contracting and Procurement | Conclude Stage
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Strategic Alignment | Review Business vision, Strategy and objectives
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Strategic Alignment | Review Commercial and Operational trends that are driving business changes
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Strategic Alignment | Review Changes to statutory, legislative or other environemtnal requirements
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Strategic Alignment | Quantify Benefits
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Review Deliverables | Assess Feasabillity
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Review Deliverables | Forecast associated costs
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Review Deliverables | Identify associated risks
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Review Deliverables | Document Possible Issues
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Review Deliverables | List Assumptions
Execution | Contracting and Procurement | Conclude Stage: Identify phase review Criteria Review Deliverables | Review Activities
Execution | Contracting and Procurement | Conclude Stage: Undertake Phase review
Execution | Contracting and Procurement | Conclude Stage: Undertake Phase review | Review Deliverables Completed to date
Execution | Contracting and Procurement | Conclude Stage: Undertake Phase review | Complete Phase review Form
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Present Vision, Objectives, Scope and Deliverables
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Discuss Current Status
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | present progress on the schedule
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Discuss deviations on Time
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Discuss Deviations on Scope
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Discuss deviations on Expenditure
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Discuss deviotions on Quality
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Discuss Key Issues
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Discuss Key Risks
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Verify project manual
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Draft project report
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Draft offer
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Hold decision meeting on release of the phase
Execution | Contracting and Procurement | Conclude Stage: Hold phase conclusion meeting | Decide on release of Stage
Execution | Contracting and Procurement | Conclude Stage: Seek Approval to Proceed
Execution | Contracting and Procurement | Conclude Stage: Seek Approval to Proceed | Approves Project to proceed
Execution | Contracting and Procurement | Conclude Stage: Seek Approval to Proceed | Request Additional Information or activities to be undertaken
Execution | Contracting and Procurement | Conclude Stage: Seek Approval to Proceed | Delay Transfer or cancel project
Execution | Contracting and Procurement | Conclude Stage: Forward Planning
Execution | Contracting and Procurement | Conclude Stage: Forward Planning | Compile and consolidate results
Execution | Contracting and Procurement | Conclude Stage: Forward Planning | Verify and refine overall project planning
Execution | Contracting and Procurement | Conclude Stage: Administer results
Execution | Contracting and Procurement | Conclude Stage: Administer results | Administer results
Execution | Contracting and Procurement | Conclude Stage Assess Stage and Plan next Stage
Execution | Contracting and Procurement | Conclude Stage: Administer results | Review, audit and report project stage
Execution | Contracting and Procurement | Conclude Stage: Administer results | Review and update project plan. Update Charter for Next Stage.
Execution | Detailed Design | Develop process and organizational concept
Execution | Detailed Design | Develop process and organizational concept | Process Design
Execution | Detailed Design | Develop process and organizational concept Process Design | Plan action for determining process and organizational concept
Execution | Detailed Design | Develop process and organizational concept Process Design | Develop process and organizational concept
Execution | Detailed Design | Develop process and organizational concept Process Design | Verify process and organizational concept (using scenarios, variants and, possibly, the prototype)
Execution | Detailed Design | Develop process and organizational concept Process Design
Execution | Detailed Design | Developing deployment and operational concepts
Execution | Detailed Design | Developing deployment and operational concepts | Define Deployment and operational concepts
Execution | Detailed Design | Developing deployment and operational concepts | Define user support
Execution | Detailed Design | Developing deployment and operational concepts | Define preparations
Execution | Detailed Design | Developing deployment and operational concepts | Determine secure operation
Execution | Detailed Design | Developing deployment and operational concepts | Organize normal operation
Execution | Detailed Design | Developing deployment and operational concepts | Describe system engineering
Execution | Detailed Design | Developing deployment and operational concepts | Define boundaries and interfaces
Execution | Detailed Design | Developing deployment and operational concepts | Define Deployment and operational concepts
Execution | Detailed Design | Deployment Planning
Execution | Detailed Design | Deployment Planning | Define and make available production environment
Execution | Detailed Design | Deployment Planning | Verify production environment
Execution | Detailed Design | Deployment Planning | Specify definition and organization of follow-up entries
Execution | Detailed Design | Deployment Planning | Define data migration and draft migration procedures
Execution | Detailed Design | Deployment Planning | Verify and refine deployment concept
Execution | Detailed Design | Deployment Planning | Verify and implement support concept
Execution | Detailed Design | Deployment Planning | Define SLA for operation and maintenance
Execution | Detailed Design | Develop training concept
Execution | Detailed Design | Develop training concept
Execution | Detailed Design | Prepare processes and organization
Execution | Detailed Design | Prepare processes and organization
Execution | Detailed Design | Prepare processes and organization | Plan action for preparing processes and organization
Execution | Detailed Design | Prepare processes and organization | Plan action for preparing processes and organization
Execution | Detailed Design | Prepare processes and organization | Plan action for preparing processes and organization
Execution | Detailed Design | Back up data
Execution | Detailed Design | Back up data | Perform backup
Execution | Detailed Design | Implement protection measures
Execution | Detailed Design | Implement protection measures | Verify and supplement ISDP concept
Execution | Detailed Design | Implement protection measures | Implement protection measures
Execution | Detailed Design | Implement protection measures | Analyze efficiency of protection measures
Execution | Detailed Design | Implement protection measures | Improve protection measures
Execution | Detailed Design | Implement protection measures | Implement protection measures step by step
Execution | Detailed Design | Implement protection measures | Implement protection measures step by step
Execution | Detailed Design | Implement protection measures | Implement protection measures step by step
Execution | Detailed Design | Train users
Execution | Detailed Design | Train users | Organize and conduct training
Execution | Detailed Design | Train users | Hold decision meeting on commissioning
Execution | Detailed Design | Draft training documentation
Execution | Detailed Design | Draft training documentation | Draw up manuals, training documentation and coaching guide
Execution | Detailed Design | Implement process and organizational concept
Execution | Detailed Design | Implement process and organizational concept | Process Implementation
Execution | Detailed Design | Implement process and organizational concept Process Implementation | Plan action for implementing process and organizational concept
Execution | Detailed Design | Implement process and organizational concept Process Implementation | Describe processes
Execution | Detailed Design | Implement process and organizational concept Process Implementation | Describe organization
Execution | Detailed Design | Activate processes and organization
Execution | Detailed Design | Activate processes and organization | Plan action for activating processes and organization
Execution | Detailed Design | Activate processes and organization | Process Activation
Execution | Detailed Design | Activate processes and organization | Process Activation
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over | Transfer Commissioning Documents for Sign-Off
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over | Hand-Over Owners Manuals, strategic spares and special tools
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over | Vendor Management for Transfer and Hand Over
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over | Facilitate Plant Hand Over between Contractor and O&M
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over | Initiate Guarantee Period
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over | Sign-Off transfer
Execution | Commissioning and Hand Over | Hand Over / Partial Hand Over | Capitalise Asset
Execution | Commissioning and Hand Over | Consolidate Documentation
Execution | Commissioning and Hand Over | Consolidate Documentation | Split Documents for Transfer to O&M and Project Office
Execution | Commissioning and Hand Over | Consolidate Documentation | Consolidate Project Sourcing Documentation
Execution | Commissioning and Hand Over | Consolidate Documentation | Transfer Documents
Execution | Commissioning and Hand Over | Consolidate Documentation | Obtain Transfer Sign-Off
Execution | Commissioning and Hand Over | Transfer sollution
Execution | Commissioning and Hand Over | Transfer sollution: Institute Warranty Periods | Institute Warranty Periods
Execution | Commissioning and Hand Over | Transfer sollution Consolidate Drawings | Consolidate Drawings
Execution | Commissioning and Hand Over | Transfer sollution Update architecture
Execution | Commissioning and Hand Over | Transfer sollution: Update architecture | Update architecture
Execution | Commissioning and Hand Over | Transfer sollution: Update Asset register
Execution | Commissioning and Hand Over | Transfer sollution: Update Asset register | Update Asset register
Execution | Commissioning and Hand Over | Transfer sollution
Execution | Commissioning and Hand Over | Transfer sollution | Transfer sollution
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Close-Out all Service Contracts
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Re-Assign Resources
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Demobilise Project Sourcing Staff and Structure
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Demolish Temporary Structures
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Transfer Permanent Structures to O&M
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Perform Final Clean-Up and Inspections
Execution | Detailed Design | Perform adaptation and extension
Execution | Detailed Design | Perform adaptation and extension | Define adaptation procedure
Execution | Detailed Design | Perform adaptation and extension | Define adaptation procedure
Execution | Detailed Design | Perform adaptation and extension | Define and make available integration and preproduction environment
Execution | Detailed Design | Perform adaptation and extension | Define and make available integration and preproduction environment
Execution | Detailed Design | Perform adaptation and extension | Perform detailed parameterization
Execution | Detailed Design | Perform adaptation and extension | Perform detailed parameterization
Execution | Detailed Design | Perform adaptation and extension | Perform extensions
Execution | Detailed Design | Perform adaptation and extension | Perform extensions
Execution | Detailed Design | Perform adaptation and extension | Build migration and interface programs
Execution | Detailed Design | Perform adaptation and extension Build migration and interface programs | Build migration and interface programs
Execution | Detailed Design | Perform adaptation and extension | Hold decision meeting on system adaptation
Execution | Detailed Design | Perform adaptation and extension | Hold decision meeting on system adaptation
Execution | Deliverable Construction | Build Execute | Project Integration Management
Execution | Deliverable Construction | Build Execute | Technical Interface Management
Execution | Deliverable Construction | Build Execute | Contract Management
Execution | Deliverable Construction | Build Execute | Manage Project Procurement Milestones and Supplies
Execution | Deliverable Construction | Build Execute | Project Management, Control and Reporting
Execution | Deliverable Construction | Build Execute | Commission Planning
Execution | Deliverable Construction | Build Execute | Erection Inspection and Checks
Execution | Deliverable Construction | Build Execute | Verify Plant is Built as per Documentation
Execution | Deliverable Construction | Accepting Deliverables Procurement management | Procurement management
Execution | Deliverable Construction | Accepting Deliverables Procurement management | Procurement management
Execution | Deliverable Construction | Accepting Deliverables Quality management | Quality management
Execution | Deliverable Construction | Accepting Deliverables Quality management | Quality management
Execution | Deliverable Construction | Accepting Deliverables Issue management | Issue management
Execution | Deliverable Construction | Accepting Deliverables Issue management | Issue management
Execution | Deliverable Construction | Accepting Deliverables Risk management | Risk management
Execution | Deliverable Construction | Accepting Deliverables Risk management | Risk management
Execution | Deliverable Construction | Accepting Deliverables Communications management | Communications management
Execution | Deliverable Construction | Accepting Deliverables Communications management | Communications management
Execution | Deliverable Construction | Accepting Deliverables Team Plan | Team Plan
Execution | Deliverable Construction | Accepting Deliverables Team Plan | Team Plan
Execution | Deliverable Construction | Accepting Deliverables Work Package | Work Package
Execution | Deliverable Construction | Accepting Deliverables Work Package | Work Package
Execution | Commissioning and Hand Over | Conduct tests
Execution | Commissioning and Hand Over | Conduct tests | Conduct acceptance tests
Execution | Commissioning and Hand Over | Conduct tests Conduct acceptance tests | Verify test plan
Execution | Commissioning and Hand Over | Conduct tests Conduct acceptance tests | Perform tests
Execution | Commissioning and Hand Over | Conduct tests Prepare assessment tests | Prepare assessment tests
Execution | Commissioning and Hand Over | Conduct tests Prepare assessment tests | Conduct assessment tests
Execution | Commissioning and Hand Over | Conduct tests | Conduct acceptance tests
Execution | Commissioning and Hand Over | Conduct tests Conduct acceptance tests | Take corrective action and optimization measures
Execution | Commissioning and Hand Over | Conduct tests Conduct acceptance tests | Conduct acceptance tests
Execution | Commissioning and Hand Over | Conduct tests Conduct acceptance tests | Hold decision meeting on acceptance of the system
Execution | Commissioning and Hand Over | Start-Up and Commissioning
Execution | Commissioning and Hand Over | Start-Up and Commissioning | Perform Safety Clearance
Execution | Commissioning and Hand Over | Start-Up and Commissioning | Perform Functional Testing
Execution | Commissioning and Hand Over | Start-Up and Commissioning | Initiate and Perform Cold Commissioning and Hot Commissioning
Execution | Commissioning and Hand Over | Start-Up and Commissioning | Do Performance and Acceptance Testing
Execution | Commissioning and Hand Over | Start-Up and Commissioning | Document Plant Performance Baseline
Execution | Commissioning and Hand Over | Start-Up and Commissioning | Verify Plant is Built as per Drawings
Execution | Commissioning and Hand Over | Start-Up and Commissioning | Verify Hand-Over Documentation and Information Set
Execution | Implementation | Site Preparation and access | Conduct Site visit and assessment
Execution | Implementation | Site Preparation and access | Conduct Site visit and assessment
Execution | Implementation | Site Preparation and access | Arrange for site access and permits
Execution | Implementation | Site Preparation and access | Arrange for site access and permits
Execution | Implementation | Build Construct The Deliverables | Create detail designs of deliverables
Execution | Implementation | Build Construct The Deliverables | Construct Deliverables
Execution | Implementation | Build Construct The Deliverables | Conformance testing on Deliverables
Execution | Implementation | Build Construct The Deliverables | Quality testing of deliverables
Execution | Implementation | Build Construct The Deliverables | Sign off and commissioning of deliverables
Execution | Implementation | Build Construct Conduct tests | Conduct acceptance tests
Execution | Implementation | Build Construct Conduct acceptance tests | Verify test plan
Execution | Implementation | Build Construct Conduct acceptance tests | Perform tests
Execution | Implementation | Build Construct Conduct acceptance tests | Conduct assessment tests
Execution | Implementation | Build Construct Conduct acceptance tests | Conduct acceptance tests
Execution | Implementation | Build Construct Conduct acceptance tests | Take corrective action and optimization measures
Execution | Implementation | Build Construct Conduct acceptance tests | Conduct acceptance tests
Execution | Implementation | Build Construct Conduct acceptance tests | Hold decision meeting on acceptance of the system
Execution | Implementation | Product delivery management | Executing A Work Package
Execution | Implementation | Product delivery management Executing A Work Package | Establish and confirm site access
Execution | Implementation | Product delivery management Executing A Work Package | Completed Work Package
Execution | Implementation | Product delivery management Executing A Work Package | Authorised Work Package
Execution | Implementation | Product delivery management Manage Detail Design | Perform Technical Clarification
Execution | Implementation | Product delivery management Manage Detail Design | Initiate and Manage Detailed Design
Execution | Implementation | Product delivery management Manage Detail Design | Perform constructability reviews
Execution | Implementation | Product delivery management Manage Detail Design | Review Detail Designs from Suppliers and OEMs
Execution | Implementation | Product delivery management Manage Detail Design | Perform Integration Management between Contractors
Execution | Implementation | Product delivery management Manage Detail Design | Perform Configuration Managament of ALL Technical Documention and Drawings
Execution | Implementation | Product delivery management Manage Detail Design | Review and Approval: Release for Manufacture and Construction
Execution | Deliverable Construction | Establish Operational Readiness | Establish O+M organisation structures and management appointments
Execution | Deliverable Construction | Establish Operational Readiness | Appoint and Allocate O+M Resources
Execution | Deliverable Construction | Establish Operational Readiness | Establish O+M Systems, Methodology, Processes and Procedures
Execution | Deliverable Construction | Establish Operational Readiness | Identify and Schedule O+M Personnel Training Requirements
Execution | Deliverable Construction | Establish Operational Readiness | Coordinate and Manage O+M Training with OEM's
Execution | Deliverable Construction | Establish Operational Readiness | Compile Operating Technical Specifications and Standards
Execution | Deliverable Construction | Establish Operational Readiness | Establish O+M Accomodation and Infrastructure
Execution | Deliverable Construction | Establish Operational Readiness | Procure Office ICT Systems, Furnishings and Ancilliary Equipment
Execution | Deliverable Construction | Establish Operational Readiness | Manage Integration of Backoffice Management Systems and Processes. Including document and records management.
Execution | Deliverable Construction | Establish Operational Readiness | Appoint Balance of O+M and Adminisrative Personnel
Execution | Deliverable Construction | Establish Operational Readiness | Identify Services to be Outsourced
Execution | Deliverable Construction | Establish Operational Readiness | Execution of Operational Service Contract Enquiries
Execution | Deliverable Construction | Establish Operational Readiness | Compile Tender Enquiry Documents
Execution | Deliverable Construction | Establish Operational Readiness | Issue, Evaluate and Award
Execution | Deliverable Construction | Establish Operational Readiness | Appoint Balance of O+M and Adminisrative Personnel
Execution | Commissioning and Hand Over | Deploy system
Execution | Commissioning and Hand Over | Deploy system Distribute and install system | Prepare and perform migration
Execution | Commissioning and Hand Over | Deploy system Distribute and install system | Hold decision meeting on system migration
Execution | Commissioning and Hand Over | Deploy system Activate system
Execution | Commissioning and Hand Over | Deploy system Activate system | Activate the computer system
Execution | Commissioning and Hand Over | Deploy system Activate system | Activate the computer system
Execution | Commissioning and Hand Over | Deploy system Activate system | Analyze deployment with operation
Execution | Commissioning and Hand Over | Deploy system Activate system | Analyze deployment with operation
Finalisation | Close Out | Conclude project marketing
Finalisation | Close Out | Conclude project marketing | Publish project successes
Finalisation | Close Out | Conclude project marketing | Draft MA final report
Finalisation | Close Out | Conclude business process modeling
Finalisation | Close Out | Conclude business process modeling
Finalisation | Close Out | Conclude business process modeling | Verify implementation and monitoring of process and organization activation
Finalisation | Close Out | Conclude business process modeling | Draft OCM final report
Finalisation | Close Out | Conclude information security and data protection
Finalisation | Close Out | Conclude information security and data protection | Describe information security process
Finalisation | Close Out | Conclude information security and data protection | Implement information security process
Finalisation | Close Out | Conclude information security and data protection | Draft ISDP final report
Finalisation | Close Out | Conclude risk management
Finalisation | Close Out | Conclude risk management | Draft RM final report
Finalisation | Close Out | Conclude configuration management
Finalisation | Close Out | Conclude configuration management | Draft CM final report
Finalisation | Close Out | Conclude configuration management
Finalisation | Close Out | Conclude configuration management | Transfer project results to maintenance organization
Finalisation | Close Out | Conclude configuration management | Draft final project evaluation
Finalisation | Close Out | Conclude configuration management | Release resources
Finalisation | Close Out | Conclude configuration management | Record project experience and hold decision meeting on project finalization
Finalisation | Close Out | Conclude quality assurance
Finalisation | Close Out | Conclude quality assurance | Draft QA final report
Finalisation | Close Out | Initiate Plant Lifecycle Plan - O&M
Finalisation | Close Out | Initiate Plant Lifecycle Plan - O&M | Compile and Implement Lifecycle Plan
Finalisation | Close Out | Identifying Follow-On Actions
Finalisation | Close Out | Identifying Follow-On Actions : Follow-on-Action Recommendations
Finalisation | Close Out | Identifying Follow-On Actions : Issue Log
Finalisation | Close Out | Identifying Follow-On Actions : Post Project Review Plan
Finalisation | Close Out | Identifying Follow-On Actions : Risk Log
Finalisation | Close Out | De-Commissioning A Project
Finalisation | Close Out | De-Commissioning A Project : Configuration Item Records
Finalisation | Close Out | De-Commissioning A Project : Configuration Management Plan
Finalisation | Close Out | De-Commissioning A Project : Customer Acceptance
Finalisation | Close Out | De-Commissioning A Project : Issue Log
Finalisation | Close Out | De-Commissioning A Project : Management Information
Finalisation | Close Out | De-Commissioning A Project : Notification of Project End
Finalisation | Close Out | De-Commissioning A Project : Operational and Maintenance Acceptance
Finalisation | Close Out | De-Commissioning A Project : Product Status Account
Finalisation | Close Out | De-Commissioning A Project : Project Closure Recommendation
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Close-Out all Service Contracts
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Re-Assign Resources
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Demobilise Project Sourcing Staff and Structure
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Demolish Temporary Structures
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Transfer Permanent Structures to O&M
Execution | Commissioning and Hand Over | Demobilise Site Office and Staff | Perform Final Clean-Up and Inspections
Finalisation | Close Out | Close-Out Project
Finalisation | Close Out | Close-Out Project | Close-Out Guarantees and Contracts
Finalisation | Close Out | Close-Out Project | Resolve Any Warrantee or Contract Administration Claims
Finalisation | Close Out | Close-Out Project | Close-Out Funding and Accounts
Finalisation | Close Out | Close-Out Project | Re-Assign Project Staff
Finalisation | Close Out | Close-Out Project | Conduct Project Execution Review
Finalisation | Close Out | Close-Out Project | Manage Documents and Archival
Finalisation | Close Out | Close-Out Project | Develop Close-Out Report
Finalisation | Close Out | Close-Out Project | Present Project Results to Approval Body
Finalisation | Evaluation | Evaluate Project Governance and Operational Delivery.
Finalisation | Evaluation | Evaluate Project Governance and Operational Delivery. | Appoint Independent Project Audit Team
Finalisation | Evaluation | Evaluate Project Governance and Operational Delivery. | Agree Audit Methods and Expected Ouputs
Finalisation | Evaluation | Evaluate Project Governance and Operational Delivery. | Execute Audit with Reference To Project Management and Delivery
Finalisation | Evaluation | Evaluate Project Governance and Operational Delivery. | Compile Project Governance and Delivery Evaluation Report
Finalisation | Evaluation | Evaluate Project Governance and Operational Delivery. | Communicate and Feedback to Shareholders / Owner
Finalisation | Evaluation | Evaluate Technical Delivery.
Finalisation | Evaluation | Evaluate Technical Delivery. | Appoint Independent Technical Audit Team
Finalisation | Evaluation | Evaluate Technical Delivery. | Agree Audit Methods and Expected Ouputs
Finalisation | Evaluation | Evaluate Technical Delivery. | Execute Technical Audit with Reference to Technical Delivery and Performance
Finalisation | Evaluation | Evaluate Technical Delivery. | Business Case and Cost Model Evaluation and Gap Analysis
Finalisation | Evaluation | Evaluate Technical Delivery. | Compile Technical Evaluation Report
Finalisation | Evaluation | Evaluate Technical Delivery. | Communicate and Feedback to Shareholders / Owner
Finalisation | Evaluation | Identify Closure Actions
Finalisation | Evaluation | Identify Closure Actions | Deliverables
Finalisation | Evaluation | Identify Closure Actions | Deliverables
Finalisation | Evaluation | Identify Closure Actions | Deliverables
Finalisation | Evaluation | Identify Closure Actions | Deliverables
Finalisation | Evaluation | Identify Closure Actions | Dcumentation
Finalisation | Evaluation | Identify Closure Actions | Dcumentation
Finalisation | Evaluation | Identify Closure Actions | Dcumentation
Finalisation | Evaluation | Identify Closure Actions | Dcumentation
Finalisation | Evaluation | Identify Closure Actions | Dcumentation
Finalisation | Evaluation | Identify Closure Actions | Suppliers
Finalisation | Evaluation | Identify Closure Actions | Suppliers
Finalisation | Evaluation | Identify Closure Actions | Resources
Finalisation | Evaluation | Identify Closure Actions | Resources
Finalisation | Evaluation | Identify Closure Actions | Communications
Finalisation | Evaluation | Identify Closure Actions | Communications
Finalisation | Evaluation | Underatke Closure Actions
Finalisation | Evaluation | Underatke Closure Actions Submit Closure Plan for Review | PM Submits Closure Plan for Review
Finalisation | Evaluation | Underatke Closure Actions Submit Closure Plan for Review | PM Submits Closure Plan for Review
Finalisation | Evaluation | Underatke Closure Actions Submit Closure Plan for Review | PM Submits Closure Plan for Review
Finalisation | Evaluation | Underatke Closure Actions Implement Closure Plan | Implement Closure Plan
Finalisation | Close Out | De-Commissioning A Project
Finalisation | Close Out | De-Commissioning A Project : Configuration Item Records
Finalisation | Close Out | De-Commissioning A Project : Configuration Management Plan
Finalisation | Close Out | De-Commissioning A Project : Customer Acceptance
Finalisation | Close Out | De-Commissioning A Project : Issue Log
Finalisation | Close Out | De-Commissioning A Project : Management Information
Finalisation | Close Out | De-Commissioning A Project : Notification of Project End
Finalisation | Close Out | De-Commissioning A Project : Operational and Maintenance Acceptance
Finalisation | Close Out | De-Commissioning A Project : Product Status Account
Finalisation | Close Out | De-Commissioning A Project : Project Closure Recommendation
Finalisation | Evaluation | Identifying Follow-On Actions
Finalisation | Evaluation | Identifying Follow-On Actions | Follow-on-Action Recommendations
Finalisation | Evaluation | Identifying Follow-On Actions | Follow-on-Action Recommendations
Finalisation | Evaluation | Confirm Project Completion
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion | review completion Criteria
Finalisation | Evaluation | Confirm Project Completion
Finalisation | Evaluation | Confirm Project Completion | Confirm Project Completion
Finalisation | Evaluation | Confirm Project Completion | Identify closure Actions
Finalisation | Evaluation | Confirm Project Completion | Undertake Closure Actions
Finalisation | Evaluation | Audit Business Plan Benefits
Finalisation | Evaluation | Audit Business Plan Benefits | Appoint Independent Audit Team
Finalisation | Evaluation | Audit Business Plan Benefits | Agree Audit Methods and Expected Outputs
Finalisation | Evaluation | Audit Business Plan Benefits | Execute Audit with Reference To Planned Benefits
Finalisation | Evaluation | Audit Business Plan Benefits | Business Case and Cost Model Evaluation and Gap Analysis
Finalisation | Evaluation | Audit Business Plan Benefits | Compile Business Evaluation Report
Finalisation | Evaluation | Audit Business Plan Benefits | Communicate and Feedback to Shareholders / Owner
Concept | Opportunity Screening | Directing a project Authorisations | Authorising an Execption Plan
Concept | Opportunity Screening | Directing a project Authorisations | Approved Exception Request
Concept | Opportunity Screening | Directing a project Authorisations | Exception Plan Request
Concept | Opportunity Screening | Directing a project Authorisations | Exception Report
Concept | Opportunity Screening | Directing a project Authorisations | Highlight Report
Concept | Opportunity Screening | Directing a project Authorisations | New Project Issues
Concept | Opportunity Screening | Directing a project Authorisations | Project Board Guidance
Concept | Opportunity Screening | Directing a project Authorisations | Request for Advice
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | Customer Acceptance
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | End Project Report
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | Follow-on-Action Recommendations
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | Lessons Learned Report
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | Operational and Maintenance Acceptance
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | Post Project Review Plan
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | Project Closure Notification
Concept | Opportunity Screening | Directing a project Confirming Project Premature Closure | Project Closure Recommendation
Concept | Pre Feasabillity | Develop a Business Case: Identify business problem | Business Vision, Strategy, Objectives
Concept | Pre Feasabillity | Develop a Business Case: Identify business problem | Newly Identified Competing Products or processes
Concept | Pre Feasabillity | Develop a Business Case: Identify business problem | Opportunities resulting from newly introduced technologies
Concept | Pre Feasabillity | Develop a Business Case: Identify business problem | Commercial and operational trends that are driving business changes
Concept | Pre Feasabillity | Develop a Business Case: Identify business problem | Changes to statutory, legislative or other environmental requirements
Concept | Pre Feasabillity | Develop a Business Case: Identify business problem | Research the business problem
Concept | Pre Feasabillity | Develop a Business Case: Identify Root Cause | Identify Root Cause
Concept | Pre Feasabillity | Develop a Business Case: Identify Root Cause | Identify Root Cause
Concept | Pre Feasabillity | Develop a Business Case: Identify Root Cause | Identify Root Cause
Concept | Pre Feasabillity | Develop a Business Case: Identify Root Cause | Identify Root Cause
Concept | Pre Feasabillity | Develop a Business Case: Identify Root Cause | Identify Root Cause
Concept | Pre Feasabillity | Develop a Business Case: Identify Root Cause | Research the business problem
Concept | Pre Feasabillity | Develop a Business Case: Situation analysis | Perform assessment of the situation
Concept | Pre Feasabillity | Develop a Business Case: Situation analysis | Develop objectives (for organization, processes and system)
Concept | Pre Feasabillity | Develop a Business Case: Situation analysis | Perform base infrastructure assessment
Concept | Pre Feasabillity | Develop a Business Case: Situation analysis | Hold decision meeting on reconciliation of objectives
Concept | Pre Feasabillity | Develop a Business Case: Develop User Requirements Specification | Develop User Requirements Specification
Concept | Pre Feasabillity | Develop a Business Case: Develop User Requirements Specification | Identify requirements
Concept | Pre Feasabillity | Develop a Business Case: Define system objectives | Perform market analysis
Concept | Pre Feasabillity | Develop a Business Case: Define system objectives | Determine and analyze system requirements
Concept | Pre Feasabillity | Develop a Business Case: Define system objectives | Consolidate and document system requirements
Concept | Pre Feasabillity | Develop a Business Case: Define system objectives | Assess coverage of system requirements
Concept | Pre Feasabillity | Develop a Business Case: Defining and Analysing Products and market offerings | Defining and Analysing Products
Concept | Pre Feasabillity | Develop a Business Case: Determine Customer Quality Expectations | Determine Customer Quality Expectations
Concept | Pre Feasabillity | Develop a Business Case: Develop list of alternative sollutions | Quantify benefits
Concept | Pre Feasabillity | Develop a Business Case: Develop list of alternative sollutions | Assess feasabillity
Concept | Pre Feasabillity | Develop a Business Case: Develop list of alternative sollutions | Forecast associated costs
Concept | Pre Feasabillity | Develop a Business Case: Develop list of alternative sollutions | Identify associated risks
Concept | Pre Feasabillity | Develop a Business Case: Develop list of alternative sollutions | Document Possible Issues
Concept | Pre Feasabillity | Develop a Business Case: Develop list of alternative sollutions | List Assumptions
Concept | Pre Feasabillity | Develop a Business Case: Rank And Evaluate Possible Sollutions Assess Financial Viabillty of proposed solutions | ROI, NPV, Payback,ROCE,IRR
Concept | Pre Feasabillity | Develop a Business Case: Rank And Evaluate Possible Sollutions | Assess proposed solutions with respect to Infrastructure security
Concept | Pre Feasabillity | Develop a Business Case: Rank And Evaluate Possible Sollutions | Rate the alternative sollutions
Concept | Pre Feasabillity | Develop a Business Case: Rank And Evaluate Possible Sollutions | Identify the recommended sollution
Concept | Pre Feasabillity | Develop a Business Case: Hold decision meeting on system requirements and solution selection | Inform Operations of proposed solutions
Concept | Pre Feasabillity | Develop a Business Case: Perform Concept Design | Perform concept design
Concept | Pre Feasabillity | Develop a Business Case: Perform Concept Design | Perform concept design
Concept | Pre Feasabillity | Develop a Business Case: Define Project Scope | Develop Project Scope Statement
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: complexity | Assess Project Complexity
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Execution Strategy | Consider EPCM, TurnKey, ETC
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Execution Strategy | Select Contracting Strategy
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Partner Identification | Execution partner Identification
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Partner Identification | Partner research
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Partner Identification | Due Diligence
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Contract Type | Consider FIDIC, NEC
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Processes and Organisational Requirements | Plan action for determining process and organization requirements
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Processes and Organisational Requirements | Verify processes
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Processes and Organisational Requirements | Determine process and organization requirements
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Configuration management | Draft CM plan
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Configuration management | Establish CM
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Configuration management | Configuration Management Plan
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Risk management | Define Project Risk management approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Risk management | Define Project Risk management approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Risk management | Define Project Risk management approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Risk management | Define Project Risk management approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Risk management | Define Project Risk management approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Risk management | Define Project Risk management approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Risk management | Define Project Risk management approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Communications and Stakeholder | Inform interest groups
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Communications and Stakeholder | Include critics in the project
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Communications and Stakeholder | Promote exchange of experience
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Communications and Stakeholder | Harmonize marketing activities
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Communications and Stakeholder | Organize marketing event
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Change management | Change management
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Change management | Assess change notification
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Change management | Decide on change procedure
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Change management | Perform change
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Change management | Conclude change
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Acceptance management | Define Acceptance Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Acceptance management | Define Acceptance Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Exception management | Identify exceptional situation
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Exception management | Assess exceptional situation and determine measures
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Exception management | Conclude exceptional situation
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Quality management | Determine relevant Quality standards
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Quality management | Implementation Approach: Quality Management
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Time management | Define Time Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Time management | Define Time Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Financial management | Financial and cost accounting
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Financial management | Financial and cost accounting
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Issue management | Define Issue Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Issue management | Define Issue Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Procurement management | Define Procurement Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Procurement management | Define Procurement Management Approach
Concept | Pre Feasabillity | Develop a Business Case: Implementation Approach: Methodology, standards and BOKS | Defined Methodology
Finalisation | Evaluation | Audit business plan benefit realisation | Audit business plan benefit realisation
Finalisation | Evaluation | Audit business plan benefit realisation | Audit business plan benefit realisation
Concept | Opportunity Screening | Stage Planning Over All | Draft and tailor stage plan
Concept | Opportunity Screening | Stage Planning: Issue management | Determine Stage Issue management activities
Concept | Opportunity Screening | Stage Planning: Issue management | Draft and tailor stage plan
Concept | Opportunity Screening | Stage Planning: Quality Management | Determine Stage QA activities
Concept | Opportunity Screening | Stage Planning: Quality Management | Gain overview of project
Concept | Opportunity Screening | Stage Planning: Quality Management | Train QA team
Concept | Opportunity Screening | Stage Planning: Quality Management | Derive Q strategy
Concept | Opportunity Screening | Stage Planning: Quality Management | Draft Q model
Concept | Opportunity Screening | Stage Planning: Quality Management | Complete QA plan
Concept | Opportunity Screening | Stage Planning: Risk management | Determine Risk Mangement Activities
Concept | Opportunity Screening | Stage Planning: Risk management | Determine project risks
Concept | Opportunity Screening | Stage Planning: Risk management | Analyze and evaluate project risks
Concept | Opportunity Screening | Stage Planning: Risk management | Define risk-reduction measures
Concept | Opportunity Screening | Stage Planning: Risk management | Draft RM report
Concept | Opportunity Screening | Stage Planning: Risk management | Analyze consequences of measures
Concept | Opportunity Screening | Stage Planning: Risk management | Revise measures
Concept | Opportunity Screening | Stage Planning: Change Management | Determine change Management Actvities
Concept | Opportunity Screening | Stage Planning: Change Management | Assess change notification
Concept | Opportunity Screening | Stage Planning: Change Management | Decide on change procedure
Concept | Opportunity Screening | Stage Planning: Change Management | Perform change
Concept | Opportunity Screening | Stage Planning: Change Management | Conclude change
Concept | Opportunity Screening | Stage Planning: Exception Management | Determine Exception Management Activities
Concept | Opportunity Screening | Stage Planning: Exception Management | Identify exceptional situation
Concept | Opportunity Screening | Stage Planning: Exception Management | Assess exceptional situation and determine measures
Concept | Opportunity Screening | Stage Planning: Exception Management | Conclude exceptional situation
Concept | Opportunity Screening | Stage Planning: Stakeholder Management | Identify Stakeholders
Concept | Opportunity Screening | Stage Planning: Stakeholder Management | Assess stakeholders Needs
Concept | Opportunity Screening | Submit Opportunities to Investment Portfolio Process | Prepare, consolidate and quality approve all opportunity material
Concept | Opportunity Screening | Submit Opportunities to Investment Portfolio Process | Submit all material to Investment Portfolio Committee
Concept | Opportunity Screening | Submit Opportunities to Investment Portfolio Process | Receive approved opportunities / projects from Investment Portfolio Committee
Concept | Pre Feasabillity | Stage Management: Exception Management | Monitor and Control Stage Exceptions
Concept | Pre Feasabillity | Stage Management: Exception Management | Identify exceptional situation
Concept | Pre Feasabillity | Stage Management: Exception Management | Assess exceptional situation and determine measures
Concept | Pre Feasabillity | Stage Management: Exception Management | Conclude exceptional situation
Concept | Pre Feasabillity | Stage Management: General Management | Make resources available
Concept | Pre Feasabillity | Stage Management: General Management | Secure training and introduction
Concept | Pre Feasabillity | Stage Management: General Management | Draft and assign work orders
Concept | Pre Feasabillity | Stage Management: General Management | Check project progress
Concept | Pre Feasabillity | Stage Management: General Management | Update project history
Concept | Pre Feasabillity | Stage Management: General Management | Guide project
Concept | Pre Feasabillity | Stage Management: Issue management | Monitor and Control Stage Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Monitor Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Monitor Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Monitor Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Escalating Project Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Escalating Project Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Escalating Project Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Escalating Project Issues
Concept | Pre Feasabillity | Stage Management: Issue management | Escalating Project Issues
Concept | Pre Feasabillity | Stage Management: Quality Management | Monitor and Control Stage QA Activities
Concept | Pre Feasabillity | Stage Management: Quality Management | Determine Stage QA activities
Concept | Pre Feasabillity | Stage ManagementStage Management: Quality Management | Determine Stage QA activities
Concept | Pre Feasabillity | Stage Management: Quality Management | Determine Stage QA activities
Concept | Pre Feasabillity | Stage Management: Quality Management | Determine Stage QA activities
Concept | Pre Feasabillity | Stage Management: Quality Management | Determine Stage QA activities
Concept | Pre Feasabillity | Stage Management: Quality Management | Draft and update project documentation
Concept | Pre Feasabillity | Stage Management: Risk management | Monitor and Control Stage Risk activities
Concept | Pre Feasabillity | Stage ManagementStage Management: Risk management | Risk management
Concept | Pre Feasabillity | Stage ManagementStage Management: Risk management | Draft RM report
Concept | Pre Feasabillity | Stage ManagementStage Management: Risk management | Revise measures
Concept | Pre Feasabillity | Stage Management: Change Management | Monitor and Control Stage Changes
Concept | Pre Feasabillity | Stage Management: Stakeholder Management | Monitor and Control Stakeholder expectations
Concept | Pre Feasabillity | Stage Management: Authorising Work Package | Authorising Work Package
Concept | Pre Feasabillity | Stage Management: Assessing Progress | Checkpoint Reports
Concept | Pre Feasabillity | Stage Management: Assessing Progress | Deliverables Checklist
Concept | Pre Feasabillity | Stage Management: Assessing Progress | Deliverables Status Account
Concept | Pre Feasabillity | Stage Management: Assessing Progress | Stage Plan
Concept | Pre Feasabillity | Stage Management: Assessing Progress | Stage Status Information
Concept | Pre Feasabillity | Stage Management: Assessing Progress | Work Package Status
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Concession
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Plan Deviation
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Product Checklist
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Project Plan
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Stage End Notification
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Stage Status Information
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Tolerance Threat
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Trigger for Project End
Concept | Pre Feasabillity | Stage Management: Reviewing Stage Status | Work Trigger
Concept | Pre Feasabillity | Stage Management: Reporting Highlights | Checkpoint Reports
Concept | Pre Feasabillity | Stage Management: Reporting Highlights | Stage Status Information
Concept | Pre Feasabillity | Stage Management: Taking Corrective Action | Plan Deviation
Concept | Pre Feasabillity | Stage Management: Taking Corrective Action | Project Board Guidance
Concept | Pre Feasabillity | Stage Management: Taking Corrective Action | Request for Advice